## Slide 1
Dabas tūrisms visiem (Introducing Nature Tourism for all- UNIGREEN)
Nr.LLI-010
Project Management meeting
25.10.-26.10.2018. in Biržai
Saldus

## Slide 2
1.Watching tower building near of Sātiņu ponds.
2. Visitor counter installation in a bird watching tower. Counter has installed.
3.Project publicity activities.
Project activities

## Slide 3
Some photos in process of construction works

## Slide 4
After…

## Slide 5
After…

## Slide 6: Project publicity
At the tower installed stand with informations about project, order rules and Warning signs.

## Slide 7
Stand in the Tower

## Slide 8: Visitor counter consists of:
SensMax SE
Data sensors
Infrared technology.
The equipment is in the protective housing
The set consists of two blocks, one of which is a transmitter, and the other is a receiver.
Sensors can store data up to 250 days.
SensMax SE/DE
Manual Data reader
Manual data collector for data collection from Sensors.
Report program who installed on computer

## Slide 9: Visitor Counter

## Slide 10: Project budget
Period |  | Planning | Actual | 
1. | Report Nr.1 | € 43 520,85 | € 20 979,67 | 
2. | Report Nr.2 | 0 | € 7 404,69 | 
3. | Report Nr.3 | € 300,16 | € 1562,50 | Tourist counter 1396,50 Management 116 +50 =166
4. | Reports Nr.4 | € 287,26 | 0 | 
 | Total | € 44108,27 | € 29 946,86 | Now Save 14 161,41

## Slide 11: Thank you for attention!
Eva Jēkobsone
eva.jekobsone@saldus.lv
+371 20267729